## project WBS monitor
project: | Examen 2020 |  | Eerste versie: | 2020-05-28
Programmeur: | Max van den Boom |  | Laatste update: | 2020-06-09
date: | 2020-06-09
WBS id | predecessor | task | requirement level (MoSCoW) | Difficulty 1=easy 5=difficult | duration, hr (plan) | duration, hr (do) | evaluation (check) | action (act)
1 |  | Interview verslag houden + opstellen van Programma van Eisen | Must | 1 | 5
2 | 1 | Projectplan | Must | 3 | 4
3 | 1,2 | Plan van Aanpak | Must | 3 | 6
4 | 1,2,3 | Wireframes | Must | 2 | 2
5 | 1,2,3,4 | Functioneel ontwerp | Must | 3 | 4
6 | 1,2,3,4,5 | technish ontwerp | Must | 3 | 4
7 | 5.6 | Database aanmaken voor webpagina | Must | 2 | 1
8 | 7 | connectie webpagina en database | Must | 2 | 2
9 | 4.5 | webpagina opmaak | Should | 1 | 4
10 | 6 | Arduino sensoren | Must | 4 | 6
11 |  | Arduino webConnectie (lokaal) | Must | 5 | 10
12 | 11 | Arduino webConnectie (online) | Must | 3 | 6
13 | 10 | Arduino fahrenheit en celcius switch | Must | 1 | 3
14 | 6 | Arduino LCD display | Must | 4 | 10
15 | 10 t/m 14 | Arduino Debug | Must | 3 | 8
16 | 10 t/m 14 | Arduino code cleanup | Should | 1 | 3
17 |  | Test cases | Must | 1 | 1
18 |  | Acceptatie test | Must | 1 | 2
19 |  | installatie | Must | 1 | 1
20 | alles | Evalutatie | Must | 3 | 2
|  |  |  | Total: | 84 | 0

## MoSCoW
M | MUST | Describes a requirement that must be satisfied in the final solution for the solution to be considered a success.
S | SHOULD | Represents a high-priority item that should be included in the solution if it is possible. This is often a critical requirement but one which can be satisfied in other ways if strictly necessary.
C | COULD | Describes a requirement which is considered desirable but not necessary. This will be included if time and resources permit.
W | WON'T | Represents a requirement that stakeholders have agreed will not be implemented in a given release, but may be considered for the future. (note: occasionally the word "Would" is substituted for "Won't" to give a clearer understanding of this choice).

## version
datum | door | versieomschrijving
2015-10-09 | kadi | originele basisversie aangepast aan ideeën van Six Sigma