## project WBS monitor
project: | Digendo Betaal methode |  | Eerste versie: | 2019-04-16
Programmeur: | Remco vd linden |  | Laatste update: | 2019-04-16
date: | 2019-04-16
WBS id | predecessor | task | requirement level (MoSCoW) | Difficulty 1=easy 5=difficult | duration, hr (plan) | duration, hr (do) | evaluation (check) | action (act)
1 |  | Interview verslag houden + opstellen van Programma van Eisen | Must | 1 | 5 | 5
2 | 1 | Projectplan | Must | 3 | 4
3 | 1,2 | Plan van Aanpak | Must | 3 | 6
4 | 1,2,3 | Wireframes | Must | 2 | 2
5 | 1,2,3,4 | Functioneel ontwerp | Must | 3 | 4
6 | 1,2,3,4,5 | technish ontwerp | Must | 3 | 4
7 | 5,6 | Het installeren van de Mollie plugins | Must | 3 | 1
8 | 7 | Het aanmaken van nieuwe controllers en het inladen van mollie op deze controllers | Must | 2 | 4
9 | 8 | Het aanpassen van de reservatie blade.php en de daarbij horende controller | Must | 4 | 4
10 | 9 | Een start maken aan de betalingen opzetten | Must | 5 | 10
11 | 1 t/m 10 | Betalingen laten werken en het geld afschrijven | Must | 5 | 10
12 | 1 t/m 11 | De informatie van betalingen opslaan in de database | Must | 5 | 7
13 | 1 t/m 12 | De informatie laten zien in het dashboard en in een aparte view | Must | 5 | 8
14 | 1 t/m 13 | Een mail sturen naar de gebruiker met de informatie van de betaling | Should | 4 | 4
15 | 1 t/m 13 | Een confirmatie laten zien aan de klant dat de betaling succesvol is afgerond | Must | 3 | 4
16 | 10, 11, 12 | De reservatie op betaald zetten in de database wanneer de betaling is afgerond | Must | 2 | 3
17 | t/m 16 | Het maken van een examen portofolio met de daartoebehorende bijlages | Must | 5 | 10
18 | Alles | Evalutatie | Must | 3 | 2
|  |  |  | Total: | 92 | 5

## MoSCoW
M | MUST | Describes a requirement that must be satisfied in the final solution for the solution to be considered a success.
S | SHOULD | Represents a high-priority item that should be included in the solution if it is possible. This is often a critical requirement but one which can be satisfied in other ways if strictly necessary.
C | COULD | Describes a requirement which is considered desirable but not necessary. This will be included if time and resources permit.
W | WON'T | Represents a requirement that stakeholders have agreed will not be implemented in a given release, but may be considered for the future. (note: occasionally the word "Would" is substituted for "Won't" to give a clearer understanding of this choice).

## version
datum | door | versieomschrijving
2015-10-09 | kadi | originele basisversie aangepast aan ideeën van Six Sigma